## 2019 Returns
BUREAU OF PUBLIC PROCUREMENT
PROCUREMENT RECORDS
PROCURING ENTITY: INFRASTRUCTURE CONCESSION REGULATORY COMMISSION, ABUJA
FINANCIAL YEAR: 2019
S/N | BASIC DATA | [6 empty] | CONTRACT AWARD | [8 empty] | CONTRACT IMPLEMENTATION
| CONTRACT DESCRIPTION (INCLUDE QUANTITY FOR GOODS) | CONTRACT TYPE | ADVERTISEMENT DATES AND MEDIA | APPROVAL AUTHORITY | PROCUREMENT METHOD | BID OPENING DATE | DATE OF COMPLETION OF FINANCIAL/TECHNICAL BIDS EVALUATION REPORT | RECOMMENDED CONTRACTOR | DATE OF CERTIFICATE OF NO OBJECTION (IF APPLICABLE) | APPROVAL DATE BY AO/PTB/MTB/FEC | DATE OF CONTRACT AWARD | AWARDED TO LOWEST TENDERER | CONTRACT PERIOD | CONTRACT EXTENSION PERIOD | CONTRACT VALUE (N) | BUDGETERY PROVISION (N) | DATE OF CONTRACT COMMENCEMENT | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | DATE OF VARIATION APPROVAL | AMOUNT OF VARIATION | AMOUNT PAID AS AT DATE | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT DATE | REMARKS
1 | Procurement of Office Stationery | LUMP SUM | 2019-05-16 | DG | National Shopping | 2019-05-22 | 2019-05-22 | Edimak Gems Ltd | NA | 2019-05-22 | 2019-05-24 | YES | One Week | NA | 2432325 | 5000000 | 2019-05-24 | NA | NA | NA | Completed | 2019-06-18 | 100%
2 | Procurement of Honda HRV Salon Cars | LUMP SUM | NA | ICRC TB | Restricted Tender | 2019-12-11 | 2019-12-11 | T H P Limited | 2019-12-31 | 2019-12-31 | 2019-12-31 | Yes | One week | NA | 34659167.4 | 36787704.8 | 2019-12-31 | NA | NA | NA | Completed | 2020-01-07 | 100%
3 | Procurement of ICT Equipment and Enterprise Management System | LUMP SUM | NA | ICRC TB | Restricted Tender | 2019-12-10 | 2019-12-10 | Bluestacks Nig Ltd | 2019-12-31 | 2019-12-23 | 2019-12-31 | Yes | One week | NA | 27171238.5 | 30000000 | 2019-12-31 | NA | NA | NA | Completed | 2019-01-07 | 100%
4 | Procurement of office Furniture | LUMP SUM | NA | ICRC TB | Restricted Tender | 2019-12-10 | 2019-12-10 | Charlotte Project Concepts Ltd | 2019-12-31 | 2019-12-23 | 2019-12-31 | Yes | One week | NA | 24820000 | 25000000 | 2019-12-31 | NA | NA | NA | Completed | 2019-01-07 | 100%
5 | Review of Concession Agreements and ICRC Governance Documents | LUMP SUM | NA | ICRC TB | Restricted Tender | 2019-12-11 | 2019-12-11 | Bluestacks Nig Ltd | 2019-12-31 | 2019-12-23 | 2019-12-31 | Yes | One Month | NA | 14671500 | 15000000 | 2019-12-31 | NA | NA | NA | Completed | 2020-02-04 | 100%
6 | Remodelling of ICRC Head Office Building | LUMP SUM | NA | ICRC TB | Restricted Tender | 2019-12-16 | 2019-12-17 | Cubes Consult Nig. Ltd | 2019-12-31 | 2019-12-19 | 2019-12-31 | Yes | 3 Months | NA | 40483957.5 | 45000000 | 2019-12-31 | NA | NA | NA | Work in Progress | 2020-03-03 | 70%