## Summary
THE PRESIDENCY
Infrastructure Concession Regulatory Commission
Summary: 2018 PROCUREMENT PLAN
S/N | Category | Amount
1 | Goods | 208940000
2 | Works | 44059708.21
3 | Consulting Services | 34200000
4 | Non-Consulting Services | 7600000
| TOTAL | 294799708.21
____________________________
Engr. Chidi Izuwah Snr.
Director General

## Goods
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
GOODS: 2018 Budget Year
|  |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
1 | Procurement of office stationeries | Plan | ICRC/PRO/GDS/01/2018 | NA | Lump Sum | 2450000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
2 | Procurement of Computer Consumables | Plan | ICRC/PRO/GDS/02/2018 | NA | Lump Sum | 3550000 | NCB | PTB | NA | POST | POST
|  | Actual |  |  |  | 0
3 | Procurement of Diesel 1st Qtr | Plan | ICRC/PRO/GDS/03/2018 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
4 | Procurement of Diesel 2nd Qtr | Plan | ICRC/PRO/GDS/04/2018 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
5 | Procurement of Diesel 3rd Qtr | Plan | ICRC/PRO/GDS/05/2018 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
6 | Procurement of Diesel 4th Qtr | Plan | ICRC/PRO/GDS/06/2018 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
7 | Procurement of Books | Plan | ICRC/PRO/GDS/07/2018 | NA | Lump Sum | 150000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
8 | Production of Executive Order Signages, ICRC and Nigerian Flags | Plan | ICRC/PRO/GDS/08/2018 | NA | Lump Sum | 500000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
9 | Printing of 2015 and 2016 Annual Reports | Plan | ICRC/PRO/GDS/9/2018 | NA | Lump Sum | 1680000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
10 | Printing of Letterhead, Continuation Sheets | Plan | ICRC/PRO/GDS/10/2018 | NA | Lump Sum | 250000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
11 | Procurement of Drivers' Uniforms | Plan | ICRC/PRO/GDS/11/2018 | NA | Lump Sum | 360000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
12 | Procurement of Sedan and Utility Motor Vehicles | Plan | ICRC/PRO/GDS/12/2018 | Lots 1 and 2 | Lump Sum | 165000000 | NCB | BPP/FEC | NA | POST | PRE
Actual
13 | Procurement of Desktop and Laptop Computers, Printers, Scanners, iPads, Smart Phones etc | Plan | ICRC/PRO/GDS/13/2018 | NA | Lump Sum | 7500000 | NCB | PTB | NA | POST | POST
Actual
14 | Procurement of office Furniture and Fittings (Executive Tables and Chairs, Visitors Chairs, Bulbs and Electrical Fittings etc) | Plan | ICRC/PRO/GDS/14/2018 | NA | Lump Sum | 12000000 | NCB | PTB | NA | POST | POST
Actual
15 | Procurement of Office Equipment (Aluminium Ladder, Split, Floor Standing and Cassette Air Conditioners, Shredders, Electric Binder, Kettle, Refridgerators, Microwaves etc) | Plan | ICRC/PRO/GDS/15/2018 | NA | Lump Sum | 7500000 | NCB | PTB | NA | POST | POST
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 208940000
Total Cost Actual

## Works
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Works: 2018 Budget Year
|  |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
1 | Partitioning of Office Spaces | Plan | ICRC/PRO/WRKS/01/2018 | NA | Lump Sum | 8500000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
2 | Head Office Remodelling | Plan | ICRC/PRO/WRKS/02/2018 | NA | Lump Sum | 35559708.21 | NCB | PTB | NA | POST | POST
Actual
| Total Cost Plan |  |  |  |  | 44059708.21
Total Cost Actual

## Consultancy Services
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Consulting Services: 2018 Budget Year
|  |  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
[10 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
1 | Information Technology Consulting Services | Plan | ICRC/PRO/CS/01/2018 | NA | Lump Sum | 2200000 | NA | DG | IC | POST | POST
|  | Actual |  |  |  | 0
2 | Comprehensive Review of Concession Agreements (43 PPP Projects) Engaging the services of 6 sector specific experts to review the contracts. | Plan | ICRC/PRO/CS/FM/02/2018 | 6 Lots | Lump Sum | 30000000 | NA | PTB | CC | POST | POST
|  | Actual |  |  |  | 0
3 | Legal Services Consulting | Plan | ICRC/PRO/CS/LS/03/2018 | NA | Lump Sum | 2000000 | NA | DG | IC | POST | POST
|  | Actual |  |  |  | 0
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 34200000
Total Cost Actual

## Non-Consultancy Services
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Non-Consulting Services: 2018 Budget Year
|  |  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
1 | Procurement of Vehicle repair and maintenance vendor | Plan | ICRC/PRO/NCS/01/2018 | NA | Lump Sum | 4200000 | NCB | PTB | NA | POST | POST
|  | Actual |  |  |  | 0
2 | Procurement of Office and IT Equipments Maintenance Vendor | Plan | ICRC/PRO/NCS/02/2018 | NA | Lump Sum | 2500000 | NCB | PTB | NA | POST | POST
|  | Actual |  |  |  | 0
3 | Procurement of Lift Maintenance Vendor | Plan | ICRC/PRO/NCS/03/2018 | NA | Lump Sum | 900000 | NS | DG | NA | POST | POST
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 7600000
Total Cost Actual