## Summary
THE PRESIDENCY
Infrastructure Concession Regulatory Commission
2019 PROCUREMENT PLAN
SUMMARY
S/N | Category | Amount
1 | Goods Capital and Non Capital Goods) | 297440000
2 | Works | 45059708.21
3 | Consulting Services | 9200000
4 | Non-Consulting Services | 1350000
| TOTAL | 353049708.21
____________________________
Engr. Chidi Izuwah Snr.
Director General/CEO

## Goods
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
GOODS: 2019 Budget Year
|  |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
1 | Procurement of office stationeries | Plan | ICRC/PRO/GDS/01/2019 | NA | Lump Sum | 2450000 | NS | DG | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 2450000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
2 | Procurement of Computer Consumables | Plan | ICRC/PRO/GDS/02/2019 | NA | Lump Sum | 3550000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 3550000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
3 | Procurement of Diesel 1st Qtr | Plan | ICRC/PRO/GDS/03/2019 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 2000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
4 | Procurement of Diesel 2nd Qtr | Plan | ICRC/PRO/GDS/04/2019 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST | 2019-05-30 | 2019-06-04 | NA | NA | NA | 2019-06-05 | 2019-06-12 | 2019-06-13 | 2019-06-15 | 2000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-25 | 2019-06-25 | HHRA | 2019-05-21
|  | Actual |  |  |  | 0
5 | Procurement of Diesel 3rd Qtr | Plan | ICRC/PRO/GDS/05/2019 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST | 2019-08-06 | 2019-08-09 | NA | NA | NA | 2019-08-13 | 2019-08-20 | 2019-08-21 | 2019-08-24 | 2000000 | NA | 2019-08-27 | 2019-08-27 | NA | 2018-08-29 | 2019-08-29 | HHRA | 2019-07-09
|  | Actual |  |  |  | 0
6 | Procurement of Diesel 4th Qtr | Plan | ICRC/PRO/GDS/06/2019 | NA | Lump Sum | 2000000 | NS | DG | NA | POST | POST | 2019-11-05 | 2019-11-07 | NA | NA | NA | 2019-11-14 | 2019-11-21 | 2019-11-28 | 2019-11-30 | 2000000 | NA | 2019-11-30 | 2019-11-30 | NA | 2018-12-03 | 2019-12-03 | HHRA | 2019-09-15
|  | Actual |  |  |  | 0
7 | Procurement of Books | Plan | ICRC/PRO/GDS/07/2019 | NA | Lump Sum | 150000 | NS | DG | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 150000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
8 | Acquisition of Finance and Monitoring office in Lagos | Plan | ICRC/PRO/GDS/08/2019 | NA | Lump Sum | 60000000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 60000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2018-06-28 | 2019-06-28 | M&P | 2019-05-14
|  | Actual |  |  |  | 0
9 | Printing of Bulletin and Annual Reports | Plan | ICRC/PRO/GDS/09/2019 | NA | Lump Sum | 1680000 | NS | DG | NA | POST | POST | [9 empty] | 1680000 | [6 empty] | M&P | 2019-05-14
|  | Actual |  |  |  | 0
10 | Acquisition of ICRC Academy | Plan | ICRC/PRO/GDS/10/2019 | NA | Lump Sum | 60000000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 60000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2018-06-28 | 2019-06-28 | M&P | 2019-05-14
|  | Actual |  |  |  | 0
11 | Printing of Letterhead, Continuation Sheets | Plan | ICRC/PRO/GDS/11/2019 | NA | Lump Sum | 250000 | NS | DG | NA | POST | POST | [9 empty] | 250000 | [6 empty] | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
12 | Procurement of Drivers' Uniforms | Plan | ICRC/PRO/GDS/12/2019 | NA | Lump Sum | 360000 | NS | DG | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 360000 | NA | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
13 | Procurement of Sedan and Utility Motor Vehicles | Plan | ICRC/PRO/GDS/13/2019 | NA | Lump Sum | 26000000 | NCB | PTB | NA | POST | PRE | 2019-05-28 | 2019-06-04 | 2019-06-12 | 2019-07-31 | 2018-08-07 | 2019-08-13 | 2019-09-10 | 2019-09-17 | 2019-10-02 | 26000000 | 2019-10-16 | 2019-10-23 | 2019-10-23 | 2019-10-30 | 2019-11-30 | 2019-11-30 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
14 | Procurement of Office Equipment (Refridgerators, Shredders, Microwaves, etc) | Plan | ICRC/PRO/GDS/14/2019 | NA | Lump Sum | 15000000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 15000000 | NA | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-06-28 | 2019-06-28 | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
15 | Procurement of Desktop and Laptop Computers, Printers, Scanners, iPads, Smart Phones etc | Plan | ICRC/PRO/GDS/15/2019 | NA | Lump Sum | 15000000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 15000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HICT | 2019-05-14
|  | Actual |  |  |  | 0
16 | Monitoring and Compliance Validation Visits | Plan | ICRC/PRO/GDS/16/2019 | NA | Lump Sum | 65000000 | NCB | PTB | NA | POST | POST | 2019-05-21 | 2019-05-23 | NA | NA | NA | 2019-05-28 | 2019-06-11 | 2019-06-12 | 2019-06-14 | 65000000 | NA | 2019-06-18 | 2019-06-18 | NA | 2019-06-28 | 2019-06-28 | HICT | 2019-05-14
|  | Actual |  |  |  | 0
17 | Procurement of office Furniture and fittings (Executive Tables and Chairs, Visitors Chairs, etc) | Plan | ICRC/PRO/GDS/17/2019 | NA | Lump Sum | 25000000 | NCB | PTB | NA | POST | POST | [9 empty] | 25000000 | [6 empty] | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
18 | Review of Concession Agreements | Plan | ICRC/PRO/GDS/18/2019 | NA | Lump Sum | 15000000 | NCB | PTB | NA | POST | POST | [9 empty] | 15000000 | [6 empty] | HHRA | 2019-05-14
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 297440000
Total Cost Actual
Note on B31: Muktar Usman: Type and model of vehicles

## Works
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Works: 2019 Budget Year
|  |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
1 | Partitioning of Office Spaces | Plan | ICRC/PRO/WRKS/01/2019 | NA | Lump Sum | 9500000 | NCB | PTB | NA | POST | POST | 2019-05-31 | 2019-06-04 | 2019-05-11 | NA | NA | NA | NA | 2019-05-11 | 2019-06-08 | 2019-06-18 | 2019-06-22 | 9500000 | NA | 2019-06-28 | 2019-06-28 | 2019-07-05 | 2019-09-28 | 2019-10-08 |  | HHRA | 2019-05-22
|  | Actual |  |  |  | 0
2 | Head Office Remodelling | Plan | ICRC/PRO/WRKS/02/2019 | NA | Lump Sum | 35559708.21 | NCB | PTB | NA | POST | POST | 2019-05-31 | 2019-06-04 | 2019-05-11 | NA | NA | NA | NA | 2019-05-11 | 2019-06-08 | 2019-06-18 | 2019-06-22 | 35559708.21 | NA | 2019-06-28 | 2019-06-28 | 2019-07-05 | 2019-09-28 | 2019-10-08 |  | HHRA | 2019-05-22
Actual
| Total Cost Plan |  |  |  |  | 45059708.21
Total Cost Actual

## Consultancy Services
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Consulting Services: 2019 Budget Year
|  |  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
[10 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
1 | Information Technology Consulting Services | Plan | ICRC/PRO/CS/01/2019 | NA | Lump Sum | 1200000 | NA | DG | IC | POST | POST | [14 empty] | 1200000 | [7 empty] | ICT
|  | Actual |  |  |  | 0
2 | Financial Consulting Servives | Plan | ICRC/PRO/CS/02/2019 | NA | Lump Sum | 6000000 | NA | PTB | CQS | POST | POST | 2019-05-28 | 2019-06-04 | 2019-06-18 | 2019-07-02 | 2019-07-16 | 2019-07-23 | 2019-07-30 | 2019-08-30 | 2019-09-13 | 2019-09-20 | 2019-09-21 | 2019-09-27 | 2019-10-04 | 2019-10-09 | 6000000 | NA | 2019-10-16 | 2019-10-16 | 2019-10-23 | 2019-11-06 | 2019-11-20 |  | CCD/P3RD/TID+/Legal | 2019-05-14
|  | Actual |  |  |  | 0
3 | Legal Services Consulting | Plan | ICRC/PRO/CS/03/2019 | NA | Lump Sum | 2000000 | NA | DG | IC | POST | POST | [14 empty] | 2000000 | [7 empty] | Legal
|  | Actual |  |  |  | 0
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 9200000
Total Cost Actual

## Non-Consultancy Services
Ministry/Department/Agency: Infrastructure Concession Regulatory Commission
Non-Consulting Services: 2019 Budget Year
|  |  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Initiation/Supervision
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | RESPONSIBLE for submission of Initiation Memo/BOQ/Specifications & Design/Adverts | Deadline for Submission of BOQ/Specifications & Designs/Adverts
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
1 | Procurement of Vehicle repair and maintenance vendor | Plan | ICRC/PRO/NCS/01/2019 | NA | Lump Sum | 450000 | NS | DG | NA | POST | POST | 2019-06-04 | 2019-05-11 | NA | NA | NA | NA | 2019-05-11 | 2019-06-08 | NA | NA | 2019-06-14 | 2019-06-18 | 2019-06-25 | 2019-06-28 | 450000 | NA | 2019-07-05 | 2019-07-05 | NA | NA | NA | 450000 | HHRA
|  | Actual |  |  |  | 0
2 | Procurement of Lift Maintenance Vendor | Plan | ICRC/PRO/NCS/02/2019 | NA | Lump Sum | 900000 | NS | DG | NA | POST | POST | [21 empty] | 900000
|  | Actual |  |  |  | 0
| Total Cost Plan |  |  |  |  | 1350000
Total Cost Actual